## 372-A-PID-00001-003-R2A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | CHECK THE REVISION. ACCORDING TO RECORDS, REVISION '1' WAS PROVIDED TO TTSJV. THUS, THE CURRENT REVISION SHOULD BE '1A'
2 | Callout | 1 | A Albalooshi | The tie-in location shall be provided for Bapco review and approval, after the site survey/ visit. Contractor shall propose without jeopardizing the operation and safety of the unit.
3 | Text Box | 1 | Mahdi Ali | RETAIN EXISTING INFORMATION. THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
4 | Text Box | 1 | Mahdi Ali | BAPCO LEGACY DRAWING NO. BRA127040 SHEET 3 ADD THE ABOVE NOTE BELOW THE DRAWING NUMBER AS WAS ORIGINALLY PROVIDED BY BAPCO. DO NOT REMOVE THIS NOTE FROM ALL THE PID PROVIDED BY BAPCO.