## 372-A-PID-00004-001-R5A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | UNIT No. CHANGED IN THE SOURCE DRAWING
2 | Text Box | 1 | Mahdi Ali | BAPCO LEGACY DRAWING NO. BRA069980 SHEET 1 ADD THE ABOVE NOTE BELOW THE DRAWING NUMBER AS WAS ORIGINALLY PROVIDED BY BAPCO. DO NOT REMOVE THIS NOTE FROM ALL THE PIDs PROVIDED BY BAPCO.
3 | Callout | 1 | Mahdi Ali | 3
4 | Callout | 1 | Mahdi Ali | CHECK THE REVISION. ACCORDING TO RECORDS, REVISION '4A' WAS PROVIDED TO TTSJV. THUS, THE CURRENT REVISION SHOULD BE '4B'
5 | Callout | 1 | A Albalooshi | The tie-in location shall be provided for Bapco review and approval, after the site survey/ visit. Contractor shall propose without jeopardizing the operation and safety of the unit.
6 | Text Box | 1 | Mahdi Ali | RETAIN EXISTING INFORMATION. THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
7 | Callout | 1 | A Albalooshi | Please indicate line number
8 | Callout | 1 | A Albalooshi | Please indicate the valve size