## 372-A-PID-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | 371M3765A
2 | Call-out | 1 | MAK | Delete
3 | Text Box | 1 | MAK | 371M3765B
4 | Callout | 1 | A Albalooshi | Please confirm the size, this has been reduced from 1" as per the FEED P&ID
5 | Cloud+ | 1 | MAK | Move inside the equipment symbol where possible
6 | Call-out | 1 | MAK | General Comment to be applied to all P&IDs: As per BMPS-A8, Section 8.4.3, Drivers Tag Nos. e.g. Motors/Turbines shall always be inserted in all P&IDs and placed below the parent equipment no. e.g. Pump/Fan/Mixer/Cooler where possible. Motor FinFan tag nos. shall always be shown where applicable.