## 372-A-PID-57004-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | A.Jabbar Mahmood | Conisder adding a sample point
2 | Callout | 1 | alexis.martinez | Locate the minimum flow line as per the other lines using all the P&ID pages from right to left.
3 | Text Box | 1 | A.Jabbar Mahmood | All incoming and outgoing streams shall have flow compensation
4 | Text Box | 1 | Ahmed Marhoon | Contractor to evaluate the need for temperature and pressure compensation on FED lines.
5 | Callout | 1 | alexis.martinez | The Battery Limit arrangements are not match with BMPS-A-50003 Battery Limit arrangements. Review and correct accordingly.
6 | Call-out | 1 | Ahmed Marhoon | Stream description to be corrected. This is an outgoing stream and shall read the destination and not the source.