## 372-A-PID-57005-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | A.Jabbar Mahmood | During EPC, a detailed P&ID distriibution sheet shall be developed
2 | Call-out | 1 | Ahmed Marhoon | Correct the direction of the arrow. Reverse.
3 | Call-out | 1 | Ahmed Marhoon | Correct the direction of the arrow. Reverse.
4 | Call-out | 1 | Ahmed Marhoon | Delete arrow. Wrong direction.
5 | Call-out | 1 | Ahmed Marhoon | Add TG to be in line with BL standard arrangement.
6 | Text Box | 1 | alexis.martinez | There is not condensate production or consumption of steam associated with FED Storage tank or pumps 372P0030A/B/C, 372P0031A/B/C, 372P0032A/B. Review the requirement of this P&ID.