## 372-A-STS-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Bapco has not received the Unit Equipment List (Item Index) for review. How to cross check the correctness/completeness of equipment numbers within this document?? Equipment List is the master index and shall be issued before issuing this document.
2 | Callout | 1 | Mahdi Ali | THIS DOCUMENT IS A CALCULATION SHEET AND NOT A STUDY. THUS THE DOCUMENT TYPE SHALL BE 'CAL' AND NOT 'STS'. CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS DOCUMENT IS A STUDY THEN THE TITLE SHOULD BE CHANGED ACCORDINGLY.
3 | Callout | 2 | Ebrahim.Deyab | New tank 372D0279 shall be included??
4 | Typewritten Text | 2 | steven.coyne | Add reference to Criticality Procedure - 000-A-PRO-50017-001
5 | Callout | 2 | David.Jimenez | Please explain the purpose of notes 1,2 and 3
6 | Callout | 2 | Saeed Taher | Please advise the reason for including the Criticality ratings for existing equipment
7 | Text Box | 2 | A Albalooshi | Please relate the criticality ratings with the inspection levels.
8 | Text Box | 2 | David.Jimenez | Related to the above, please clarify whether the inspections levels are going to be defined in this document or a separate one.
9 | Cloud+ | 2 | MAK | Include pumps motors: 372M3753A 372M3753B 372M3765A 372M3765B
10 | Cloud+ | 2 | MAK | Why 301 including in 372?
11 | Text Box | 2 | MAK | General Comment: Equipment List for Unit 372 was not issued for review. However, this list shall perfectly match Unit 372 - Equipment List (Item Index). All Units equipment shall be included for Criticality Rating Evaluation.