## 372-A-STS-57001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | Mohamed Ayyash | Project number missing
2 | Callout | 1 | Mahdi Ali | INCORRECT DOCUMENT TYPE FOR CALCULATION SHEET. USE 'CAL'
3 | Cloud+ | 1 | Mohamed Ayyash | Unit name/number missing
4 | Text Box | 1 | MAK | 372P3733A 372P3733B 372P3745A 372P3745B 372M3753A 372M3753B 372M3765A 372M3765B 372V0035
5 | Text Box | 1 | MAK | General Comment: The equipment nos. in this document shall perfectly match the Equipment List (Item Index). Add the missing equipment.
6 | Text Box | 1 | MAK | General Comment: For all documents, use the latest document template that is part of the Homogenisation Procedure.
7 | Call-out | 1 | MAK | Missing Equipment 372P3733A 372P3733B 372P3745A 372P3745B 372M3753A 372M3753B 372M3765A 372M3765B 372V0035
8 | Callout | 2 | Fernando.Perez | Motors to be included in Critically Rating
9 | Text Box | 2 | alexis.martinez | Include all the equipments in the Unit
10 | Text Box | 2 | alexis.martinez | Include in the document the notes, reference and the meaning of all the abbreviations for clarity of the document.