## 372-C-DAT-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | BFW & CONDEN.DISTR (DEAERATOR)
2 | Cloud+ | 1 | MAK | BFW & CONDEN.DISTR (DEAERATOR)
3 | Text Box | 1 | MAK | Change on all sheets
4 | Cloud+ | 2 | MAK | 372 - BFW & CONDEN.DISTR (DEAERATOR)
5 | Callout | 2 | David.Jimenez | MAWP provided shall have sufficient margin against max operating conditions
6 | Callout | 2 | David.Jimenez | Please fill out
7 | Callout | 2 | David.Jimenez | Please fill out
8 | Callout | 3 | David.Jimenez | be
9 | Callout | 3 | David.Jimenez | Is this supposed to be also a choice between 2 options?
10 | Callout | 3 | David.Jimenez | Meant #150? However note that there are also #300 nozzles in nozzle schedule
11 | Callout | 3 | David.Jimenez | This data sheet should state whether fireproofing applies to 2 sides or external side only (for skirt case)
12 | Callout | 4 | David.Jimenez | be
13 | Text Box | 4 | David.Jimenez | The text quality is very poor and difficult to read. Please improve it.