## 372-C-DAT-55003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | Sameer.Ahmed | As per new 370 unit number, this equipment was assigned 370V0004. However, since this vessel is simply a storage tank, the tag number shall be 370D0007
2 | Text Box | 1 | MAK | General Comment: This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used for all Unfired Pressure Vessels.
3 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
4 | Call-out | 1 | Mahdi Ali | Unit number shall be finalized
5 | Callout | 2 | Saeed Taher | B7 or B7M as to be consistent with removable internal piping material
6 | Callout | 2 | Julio.Aguilar | Note 13
7 | Callout | 2 | Saeed Taher | Note 6 apply
8 | Cloud+ | 2 | Sameer.Ahmed | Update tag number as indicated in sheet 1
9 | Cloud+ | 2 | Sameer.Ahmed | Update tag number as indicated in sheet 1
10 | Text Box | 3 | Julio.Aguilar | Add note 13: " Vessel steam out conditions"
11 | Cloud+ | 3 | Julio.Aguilar | It shall be responsibility of the manufacturer to complete the datasheet where the information is not filled.
12 | Text Box | 3 | JaiMun.Oh | The external surface shall be painted as per BMPS-B5.
13 | Cloud+ | 3 | Sameer.Ahmed | Update tag number as indicated in sheet 1
14 | Cloud+ | 4 | Sameer.Ahmed | Update tag number as indicated in sheet 1
15 | Text Box | 5 | Julio.Aguilar | Ensure vent and drain sizing follow BMPS-A3
16 | Cloud+ | 5 | Sameer.Ahmed | Update tag number as indicated in sheet 1
17 | Cloud+ | 5 | Sameer.Ahmed | Update tag number as indicated in sheet 1