## 372-C-DAT-55006-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 3 | Ebrahim.Deyab | Add Note 23
2 | Callout | 3 | Ebrahim.Deyab | Add Note 24
3 | Callout | 4 | Julio.Aguilar | Add the manholes in the table, sheet 2.
4 | Callout | 2 | Ebrahim.Deyab | Add, LG from oil separator tanks D1015/1014 via P3733A/B.
5 | Callout | 3 | Julio.Aguilar | Add: in later stage of the project
6 | Cloud+ | 3 | BD Mori | Check and revise if required based on the 1/2 SGP design during EPC phase.
7 | Callout | 2 | Salman Jaffer | Check the equipment number
8 | Cloud+ | 1 | Sameer.Ahmed | DISTRIBUTION
9 | Text Box | 1 | Julio.Aguilar | Ensure the use of the project finalized cover page for the all data sheets.
10 | Text Box | 1 | MAK | General Comment: This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used for all Unfired Pressure Vessels.
11 | Text Box | 4 | Ebrahim.Deyab | Is blanketing steam needed? Vendor to verify.
12 | Cloud+ | 4 | Julio.Aguilar | L1A
13 | Callout | 2 | Zosimo | Level, Pressure & Temperature instruments connections size and type should comply with BMPS-J2 Section 8.1 Process Connections
14 | Callout | 1 | Sameer.Ahmed | Move it up
15 | Callout | 2 | Julio.Aguilar | Overflow line sizing to be confirmed by vendor. Basis for this figure to be indicated.
16 | Callout | 2 | Ebrahim.Deyab | Paralleling/equalizing connection line between vessels A&B to be be added.
17 | Cloud+ | 3 | Julio.Aguilar | remove this statement
18 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
19 | Callout | 2 | Julio.Aguilar | The numbering of the nozzles shall be uniform throughout the entire project. e.g. N1, N2, N3...etc. Correct properly.
20 | Text Box | 4 | Julio.Aguilar | The numbering of the nozzles shall be uniform throughout the entire project. e.g. N1, N2, N3...etc. Correct properly.
21 | Text Box | 1 | Sameer.Ahmed | This vessel datasheet template is not consistent with other datasheets provided by SOC or TTSJV. It should be revised as per the Homogenization Procedure.
22 | Cloud+ | 1 | Sameer.Ahmed | Use the latest equipment numbering and unit number (370) as provided (applicable to all pages of this specification sheet)
23 | Cloud+ | 3 | BD Mori | What is the difference between these two streams? As per 044-A-PFD-00001-010 steam #332, flow is 740.034 Mlb/hr. Check and revise as required.