## 372-D-DAT-57079-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comment: Use the latest cover sheet which is part of the Homogenization Procedure. TR shall coordinate with JV Directorate.
2 | Text Box | 1 | alexis.martinez | General: All Equipment Numbers need to be updated as per the new numbering provided by owner.
3 | Cloud+ | 2 | Mohamed Ayyash | Align boxes with text for better representation
4 | Cloud+ | 2 | Mohamed Ayyash | Align boxes with text for better representation
5 | Text Box | 2 | Mahdi Ali | Align Text to avoid overlap
6 | Text Box | 2 | Mahdi Ali | Change to 372-A-PID-00004-003
7 | Callout | 2 | alexis.martinez | Page 2. Tank capacity is not matching with PFD 372-A-PFD-54001-001. Review and do the required corrections.
8 | Callout | 2 | alexis.martinez | Page 2. Tank height is not matching with height on PFD 372-A-PFD 372-A-PFD-54001-001 and P&ID 372-A-PID-57001-001. Review and do the required corrections.
9 | Callout | 2 | Abdul Rahim | power and Utilities
10 | Callout | 3 | Abdul Rahim | all unit should be in SI
11 | Text Box | 3 | Mahdi Ali | Requires proper formatting
12 | Callout | 4 | Abdul Rahim | all units should be in SI
13 | Cloud+ | 5 | Mohamed Ayyash | Move to center of cell
14 | Callout | 5 | alexis.martinez | Page 5. Include as per commented P&ID 372-A-PID-57001-001 and commented General arrangement 372-D-GAD-57079-001 (4 sheets), the number of nozzles and size
15 | Cloud+ | 5 | Mohamed Ayyash | Write "Datum" on one line. Adjust font or column width
16 | Cloud+ | 5 | Mohamed Ayyash | Write "Dimension" and "Finish" on one line. Adjust font or column width
17 | Cloud+ | 5 | Mohamed Ayyash | Write "schedule" on one line. Adjust font or column width
18 | Cloud+ | 6 | Mohamed Ayyash | Move to center of cell
19 | Callout | 6 | alexis.martinez | Pages 5 and 6. Move the sections 24,25,26,27 and 28 after section 23. Avoid split table 3 to insert section in between
20 | Cloud+ | 6 | Mohamed Ayyash | Write "Dimension" and "Finish" on one line. Adjust font or column width
21 | Cloud+ | 6 | Mohamed Ayyash | Write "schedule" on one line. Adjust font or column width
22 | Callout | 8 | alexis.martinez | Page 8. The Tank Height is not matching with PFD and P&ID. Review and do the required corrections.
23 | Text Box | 9 | Ahmed Marhoon | Location of nozzles for the level instruments shall be firmed post detail design/Hazop/SIL by the TTSJV taking into account the hold-up volume/surge volume and residence time specified for BMP.
24 | Text Box | 9 | Ahmed Marhoon | Measuring range/span of both level transmitters shall be identical to avoid saturation and loss of control measurement/indication during abnormal condition. Location of the 2CNB Nozzle to be changed accordingly.
25 | Text Box | 9 | Ahmed Marhoon | Nitrogen pressure control on this tank has been commented on the respective P&ID. Resolution on those comments to be reflected on the Data Sheet as applicable.
26 | Callout | 9 | alexis.martinez | Page 5. Include as per commented P&ID 372-A-PID-57001-001 and commented General arrangement 372-D-GAD-57079-001 (4 sheets), the number of nozzles and size
27 | Text Box | 11 | Mahdi Ali | Inconsistent Tagging
28 | Callout | 11 | alexis.martinez | Page 11, Note 15. This is the revision A, hence empty notes are not used.