## 372-D-GAD-55002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | Julio.Aguilar | Add Note 11 here
2 | Cloud+ | 1 | Julio.Aguilar | Update with the approved numbering for the unit 370
3 | Cloud+ | 1 | Basheer.isa | pressure, temperature and level instrument connection to be as per BMPS-J2, sec 8.1
4 | Cloud+ | 1 | Sameer.Ahmed | unit 370
5 | Cloud+ | 1 | Sameer.Ahmed | Drawing number to be revised being it is part of unit 370
6 | Callout | 1 | Julio.Aguilar | Ensure vent sizing follows BMPS-A3 criteria
7 | Text Box | 1 | Mahdi Ali | 1. Use latest border that is part of the Homogenization procedure. 2. Include equipment tag number in all sheets.
8 | Cloud+ | 1 | Sameer.Ahmed | This is now part of new unit 370.Hence, use the latest equipment number provided for unit 370.
9 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.