## 372-D-GAD-55003-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | 1. Use latest border that is part of the Homogenization procedure. 2. Include equipment tag number in all sheets.
2 | Callout | 1 | Robert.Kawitzki | Make 900 as per BMPS A4
3 | Cloud+ | 1 | Sameer.Ahmed | Drawing number to be revised being it is part of unit 370
4 | Callout | 1 | Robert.Kawitzki | Which nozzle is this dim for?
5 | Callout | 1 | Robert.Kawitzki | Walkways to be shown when nozzle locations have been finalized BMPS A5 3.7.1.2
6 | Cloud+ | 1 | Sameer.Ahmed | Unit 370
7 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
8 | Cloud+ | 1 | Sameer.Ahmed | Why "Hold"
9 | Cloud+ | 1 | Julio.Aguilar | Update with unit 370