## 372-D-GAD-57079-003-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | alexis.martinez | Review the liquid level DMHL, HHLL and HLL and do the correction accordingly
2 | Callout | 1 | Erwin.Lugue | Anchor bolts shall be as per BMPS-Q-141752
3 | Callout | 1 | alexis.martinez | Pressure vacuum relief valve nozzle should be only one and here are shown 3 nozzles. Review and do the correction accordingly.
4 | Cloud+ | 1 | Khalid | This normal goose neck vent. How N2 pressure is maintained?
5 | Callout | 1 | alexis.martinez | Review the tank height. It is not matching the height shown on sheet 1 (372-D-GAD-57079-001). Correct accordingly.