## 372-E-DAT-55001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | Julio.Aguilar | Follow the equipment list approved by the project for the new unit 370
2 | Text Box | 1 | Julio.Aguilar | Ensure the use of the project finalized cover page for the all data sheets.
3 | Text Box | 1 | Sang.Hwang | Contractor to confirm if this data sheet format instead of API 662 data sheet format has been approved by the Owner.
4 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
5 | Text Box | 2 | Sang.Hwang | To add corrosion allowance for connection parts. This is typical for all plate and frame type heat exchanger.
6 | Cloud+ | 2 | Julio.Aguilar | Values are different to the FEED data sheet. Confirm.
7 | Callout | 2 | Sang.Hwang | All blank shall be filled with "N/A" or "-" or "Note (X)" or "by Vendor" etc. This typical for plate and frame heat exchangers.
8 | Cloud+ | 3 | Julio.Aguilar | Values are different to the FEED data sheet. Confirm.
9 | Cloud+ | 4 | Julio.Aguilar | Values are different to the FEED data sheet. Confirm.
10 | Cloud+ | 5 | Julio.Aguilar | Ensure these cleanable filtering elements are shown also in the PIDs to be consistent.
11 | Callout | 5 | BD Mori | How filter elements will be maintained? How to decide when to clean the filter element? Differential pressure indication required? Also spare filter for changeover and maintenance? Specify these requirements.
12 | Callout | 5 | Julio.Aguilar | Add: wt
13 | Callout | 5 | Sang.Hwang | To revise as per comment on 1st page of this data sheet.
14 | Text Box | 5 | JaiMun.Oh | The external surface shall be painted as per BMPS-B5.
15 | Callout | 5 | Julio.Aguilar | Add: Total dissolved solids (TDS) 5 ppm wt max/