## 372-E-DAT-55003-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Sang.Hwang | Refer to typical comment on 372-E-DAT-55001-001 of transmittal no. : CON-BMP-TRA-070232.
2 | Cloud+ | 1 | Julio.Aguilar | Follow the equipment list approved by the project for the new unit 370
3 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
4 | Text Box | 1 | Julio.Aguilar | Ensure the use of the project finalized cover page for the all data sheets.
5 | Cloud+ | 2 | Julio.Aguilar | Values are different to the FEED data sheet. Confirm.
6 | Cloud+ | 3 | Julio.Aguilar | Values are different to the FEED data sheet. Confirm.
7 | Cloud+ | 5 | Julio.Aguilar | Ensure these cleanable filtering elements are shown also in the PIDs to be consistent.
8 | Callout | 5 | BD Mori | How filter elements will be maintained? How to decide when to clean the filter element? Differential pressure indication required? Also spare filter for changeover and maintenance? Specify these requirements.
9 | Callout | 5 | Julio.Aguilar | Add: wt
10 | Callout | 5 | Julio.Aguilar | Confirm basis of this pH range
11 | Callout | 5 | Sang.Hwang | It shall be revised as commented on 372-E-DAT-55001-001 in transmittal no. : CON-BMP-TRA-070232.