## 372-G-DAT-50002-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | Change on all pages to: BFW & CONDEN.DISTR(DEAERATOR)
2 | Cloud+ | 1 | MAK | Use correct equipment tag no. Change on all pages to: 372P3745A/B
3 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
4 | Text Box | 2 | David.Jimenez | LV motors datasheets will be attached to MR as blank form to be filled in by Vendor during engineering, as they will be purchased under umbrella contract.
5 | Callout | 3 | A Albalooshi | Coupling with hydraulic fit is required as per FEED data sheet
6 | Text Box | 3 | Isamu | Please refer to API 610 parag 6.4.2.3 and check if the minimum rating of 150# is allowable for an API pump
7 | Callout | 3 | A Albalooshi | Please advise why suction pressure regions designed for MAEP is not required. This was in FEED Data sheet
8 | Callout | 5 | A Albalooshi | Required as per FEED data sheets
9 | Callout | 5 | A Albalooshi | Required as per FEED data sheets