## 372-G-DAT-54003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Ebrahim.Deyab | Pumps number to be verified with final numbering.
2 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
4 | Callout | 2 | Ebrahim.Deyab | Clarify, pump max. is less than rated.??
5 | Text Box | 2 | Julio.Aguilar | Final figures shall be updated when the final hydraulic calculation is finalized
6 | Text Box | 2 | hyunjin.paeng | To be specified
7 | Text Box | 4 | hyunjin.paeng | AVL
8 | Callout | 7 | Julio.Aguilar | Pumps number to be verified with final numbering approved.