## 372-G-DAT-54005-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Ebrahim.Deyab | Pumps number to be verified with final numbering. | Noted. Item no. is changed to 370P0008A/B/C. | Y
2 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status. | Noted. | Y
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used. | Noted. Template will be updated in next revision. | Y
4 | Cloud+ | 2 | Julio.Aguilar | Confirm reasons of the change vs ITB process data sheet. Was the Clarification T131 considered?. | It will be updated in next revision. | Y
5 | Text Box | 2 | hyunjin.paeng | Driver type To be specified | Noted. Turbine and Motor both are specified. | Y
6 | Text Box | 2 | Julio.Aguilar | Final figures shall be updated when the final hydraulic calculation is finalized | Noted. It will be updated when hydraulic calculation is finalized. | Y
7 | Callout | 3 | Saeed Taher | Add Note (9) | Noted. | Y
8 | Cloud+ | 7 | Julio.Aguilar | Turbine tag number to be revised as per the final numbering approved. | Noted. Turbine item no. is changed to 370T0008A/B. | Y