## 372-G-DAT-54006-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Ebrahim.Deyab | Pumps number to be verified with final numbering. | Noted. Item no. changed to 370P0012A/B/C. | Y
2 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status. | Noted. | Y
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used. | Noted. Template will be updated in next revision. | Y
4 | Text Box | 2 | hyunjin.paeng | Driver type To be specified | Noted. Turbine and motor both are specified. | Y
5 | Text Box | 2 | Julio.Aguilar | Final figures shall be updated when the final hydraulic calculation is finalized | Noted. It will be updated when hydraulic calculation is finalized in next revision. | N
6 | Text Box | 3 | hyunjin.paeng | and BMPS-G10 | Noted. It is added as note. | Y
7 | Text Box | 3 | hyunjin.paeng | To be defined/confirmed by vendor | Noted. LO system will be clarified with vendor. | Y
8 | Text Box | 4 | hyunjin.paeng | AVL | Noted. | Y
9 | Cloud+ | 7 | Julio.Aguilar | Turbine tag number to be revised as per the final numbering approved. | Noted. Turbine item no. is changed to 370T0012A/B. | Y