## 372-G-DAT-54007-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Isamu | Please use project finalized cover page for the all data sheets. | noted. Revised template will be used in Rev_C | N
2 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status. | noted. | Y
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used. | noted. Revised template will be used in Rev_C | N
4 | Text Box | 2 | hyunjin.paeng | 11000 | noted | Y
5 | Text Box | 2 | Sameer.Ahmed | Dust | noted | Y
6 | Text Box | 2 | Julio.Aguilar | Final figures shall be updated when the final hydraulic calculation is finalized | It will be updated in next revision. | N
7 | Callout | 2 | Sameer.Ahmed | Insert electrical area classification | noted | Y
8 | Callout | 2 | Isamu | Name / Number please | noted | Y
9 | Cloud+ | 3 | Sameer.Ahmed | Indicate a note AVL (From approved vendor list) | noted | Y
10 | Text Box | 4 | hyunjin.paeng | AVL | noted | Y
11 | Cloud+ | 5 | Saeed Taher | Verify type of inspections for welds and castings as per applicable standards | All of inspections as per each Item Critical rating. it is mentioned in ITP | N