## 372-G-DAT-54007-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Isamu | Please use project finalized cover page for the all data sheets.
2 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
4 | Text Box | 2 | hyunjin.paeng | 11000
5 | Text Box | 2 | Sameer.Ahmed | Dust
6 | Text Box | 2 | Julio.Aguilar | Final figures shall be updated when the final hydraulic calculation is finalized
7 | Callout | 2 | Sameer.Ahmed | Insert electrical area classification
8 | Callout | 2 | Isamu | Name / Number please
9 | Cloud+ | 3 | Sameer.Ahmed | Indicate a note AVL (From approved vendor list)
10 | Text Box | 4 | hyunjin.paeng | AVL
11 | Cloud+ | 5 | Saeed Taher | Verify type of inspections for welds and castings as per applicable standards