## 372-G-DAT-54009-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Isamu | Please use project finalized cover page for the all data sheets. | noted. Revised template will be used in Rev_C | N
2 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status. | noted. | Y
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used. | noted. Revised template will be used in Rev_C | N
4 | Text Box | 2 | hyunjin.paeng | 11000 | noted | Y
5 | Cloud+ | 2 | Khalid | 1760gpm as per ITB docs?! | It will be updated in next revision. | N
6 | Text Box | 2 | Julio.Aguilar | Final figures shall be updated when the final hydraulic calculation is finalized | It will be updated in next revision. | N
7 | Cloud+ | 2 | Julio.Aguilar | HP value is lower to FEED process data sheet figure. What are the reason of the change? Confirm. Ensure the HP value is consistent for all relevant documents. e.g. PID, PDS, etc. | It will be updated in next revision. | N
8 | Callout | 2 | Sameer.Ahmed | Insert electrical area classification | noted | Y
9 | Callout | 2 | Isamu | Name / Number please | noted | Y
10 | Callout | 2 | Isamu | The maximum is less than the normal ??? Correct please | maximum pressure is revised. It will be confirmed by SECL process. | Y
11 | Callout | 2 | Julio.Aguilar | Value to be revised and confirmed | It will be updated in next revision. | N
12 | Cloud+ | 3 | Sameer.Ahmed | Indicate a note AVL (From approved vendor list) | noted | Y
13 | Text Box | 4 | hyunjin.paeng | AVL | noted | Y
14 | Cloud+ | 5 | Saeed Taher | Type of inspections for welds & castings shall comply with applicable codes. This is applicable to all data sheets | All of inspections as per each Item Critical rating. it is mentioned in ITP | N
15 | Text Box | 7 | Sankara | FEED area classification drawing shows these pumps just outside the border of Zone 2. A minor change in the plot plan can make these in hazardous area. | It will be updated in next revision. | N
16 | Cloud+ | 7 | Jong.Ahn | replace with " electric motor and steam turbine driven pumps." | noted | Y
17 | Cloud+ | 7 | Julio.Aguilar | Turbine tag number to be revised as per the final numbering approved. | noted | Y