## 372-G-DAT-54009-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Isamu | Please use project finalized cover page for the all data sheets.
2 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
4 | Text Box | 2 | hyunjin.paeng | 11000
5 | Cloud+ | 2 | Khalid | 1760gpm as per ITB docs?!
6 | Text Box | 2 | Julio.Aguilar | Final figures shall be updated when the final hydraulic calculation is finalized
7 | Cloud+ | 2 | Julio.Aguilar | HP value is lower to FEED process data sheet figure. What are the reason of the change? Confirm. Ensure the HP value is consistent for all relevant documents. e.g. PID, PDS, etc.
8 | Callout | 2 | Sameer.Ahmed | Insert electrical area classification
9 | Callout | 2 | Isamu | Name / Number please
10 | Callout | 2 | Isamu | The maximum is less than the normal ??? Correct please
11 | Callout | 2 | Julio.Aguilar | Value to be revised and confirmed
12 | Cloud+ | 3 | Sameer.Ahmed | Indicate a note AVL (From approved vendor list)
13 | Text Box | 4 | hyunjin.paeng | AVL
14 | Cloud+ | 5 | Saeed Taher | Type of inspections for welds & castings shall comply with applicable codes. This is applicable to all data sheets
15 | Text Box | 7 | Sankara | FEED area classification drawing shows these pumps just outside the border of Zone 2. A minor change in the plot plan can make these in hazardous area.
16 | Cloud+ | 7 | Jong.Ahn | replace with " electric motor and steam turbine driven pumps."
17 | Cloud+ | 7 | Julio.Aguilar | Turbine tag number to be revised as per the final numbering approved.