## 372-G-DAT-57001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
2 | Callout | 1 | Fernando.Perez | Change it for EQUIPMENT DATA SHEET
3 | Callout | 2 | alexis.martinez | GENERAL: For decimal separator use dot (.) instead of coma (,)
4 | Callout | 2 | Fernando.Perez | Change it for EQUIPMENT DATA SHEET
5 | Cloud+ | 2 | Mohamed Ayyash | Cooling water is the stream name and not the source. Need to specify the plant where it is coming from.
6 | Text Box | 2 | alexis.martinez | GENERAL: Review pumps calculations. The data is not matchming with FEED, neither with EPC P&ID data block
7 | Callout | 2 | alexis.martinez | Vacuum suction pressure is not allowed. Review the suction pressure.
8 | Callout | 2 | Fernando.Perez | Check Group.
9 | Callout | 2 | Fernando.Perez | Use capital "NOMINAL, change template in exceel
10 | Callout | 2 | Berik.Nurbolatov | Please provide H2S and corrosion data
11 | Text Box | 2 | Abdulaziz | API 610 edition shall be indicated
12 | Callout | 2 | Berik.Nurbolatov | Please update for the next revision;Voltage data
13 | Text Box | 2 | A.Jabbar Mahmood | General: Use decimal points instead of commas as decimal separator
14 | Callout | 2 | alexis.martinez | Page 2, rows 33/34. Inconsistency of maximum ambient temperature and relative humidity shown in page 2 and page 8. Review and correct
15 | Call-out | 3 | Abdulaziz | Bearing housing & bearings shall be designed for oil mist lubrication in compliance to BMPS G8.
16 | Text Box | 3 | Abdulaziz | ISO VG 68 shall be considered as an option.
17 | Callout | 3 | Fernando.Perez | Coupling Guard Required Acc BMPS-G2
18 | Callout | 3 | Fernando.Perez | Flanged & Valved Acc BMPS-G2 & BMPS-SD-G-10289
19 | Text Box | 3 | Abdulaziz | Pump DBSE shall be greater than the cartridge seal length to facilitate insitu seal repair
20 | Callout | 3 | Berik.Nurbolatov | Nozzle size and rating: Update for the next revision.
21 | Callout | 3 | Fernando.Perez | Baseplate Acc GD-G1368-0
22 | Text Box | 4 | Abdulaziz | Bearings temperature shall be included
23 | Callout | 5 | Erwin.Lugue | Equivalent weight in S.I. units to be provided
24 | Callout | 5 | Fernando.Perez | Acc Feed Data Sheet most of the test marked as observed should be witnessed Inspection Level 3. & Acc 2520-z000-PP611_0 the criticality Ranking is C (Insp.Level 3).Check
25 | Call-out | 5 | Abdulaziz | Yes
26 | Text Box | 6 | Abdulaziz | Typo
27 | Callout | 7 | Fernando.Perez | Check Group should be Group II
28 | Callout | 7 | Fernando.Perez | Accelerometer Required for motor Acc BMPS-A3 Parag.8.5
29 | Callout | 7 | Fernando.Perez | Instrumentation for driver shall be Acc BMPC-A3 / G2 & API 670
30 | Cloud+ | 7 | Khalid | A/B/C
31 | Callout | 9 | Fernando.Perez | Change redaction to: NPSHr shall be less than NPSHa at lesat in 1.4 m(4 ft)
32 | Cloud+ | 9 | Ahmed.Marhoon | A clarification required from Contractor for deleting technical notes from Datasheet. One of the notes was regarding requirement of instrumentation scope which has been excluded in the new revision. Also, the system to capture requirements for the instrumentation and control scope on relevant RFI documents, to be discussed and agreed with the Contractor.
33 | Callout | 9 | Fernando.Perez | Driver to be sized to cover End Of Curve
34 | Text Box | 9 | Ebrahim.Deyab | Autostart is provided for electric motor driven pumps
35 | Text Box | 9 | Abdulaziz | Minimum flow by pass shall be reviewed for these pumps
36 | Text Box | 9 | Abdulaziz | M/SEAL vendor shall be provided with operating parameter during, start-up/shutdown mode, study state condition an upset in order to provide the optimum design selection.