## 372-G-DAT-57003-001-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Fernando.Perez | Change it by EQUIPMENT DATA SHEET
2 | Call-out | 1 | Mahdi Ali | Remove space between equipment sequence number and suffix
3 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
4 | Text Box | 2 | Abdulaziz | All comments indicated on 012-G-DAT-00004/5-001 shall be adopted on this document
5 | Callout | 2 | Fernando.Perez | Change it by EQUIPMENT DATA SHEET
6 | Callout | 2 | Fernando.Perez | Check Group & Temp. Class
7 | Callout | 2 | Julio.Aguilar | Confirm this values. Figures in the FEED data sheet are different
8 | Cloud+ | 2 | Mohamed Ayyash | Cooling Water source ?
9 | Text Box | 2 | alexis.martinez | GENERAL: Review the the entire operating conditions. The values are not matching with EPC P&ID equipment data block.
10 | Callout | 2 | alexis.martinez | Page 2, rows 32/33. Inconsistency of maximum ambient temperature and relative humidity shown in page 2 and page 7. Review and correct
11 | Callout | 2 | Fernando.Perez | Use capital "NOMINAL" change it in the excel format
12 | Callout | 2 | alexis.martinez | Vacuun suction pressure is not allowe. Review utility water pumps circuit.
13 | Callout | 3 | Fernando.Perez | Baseplate Acc GD-G1368-0
14 | Callout | 3 | Fernando.Perez | Coupling Guard Required Acc BMPS-G2
15 | Callout | 3 | Fernando.Perez | Flanged & Valved Acc BMPS-G2
16 | Callout | 5 | Erwin.Lugue | Equivalent weight in S.I. units to be provided
17 | Callout | 7 | Fernando.Perez | Group Should be II and Temp class T6, check and confirm
18 | Cloud+ | 7 | Mohamed Ayyash | This is a site location and not unit names. It is asking for service for units and therefor need to mention those units names.
19 | Callout | 8 | Yousif Ahmadi | Add: "Cooling water piping (if any) materials shall be as per indicated on document BMPS-L2."
20 | Callout | 8 | Fernando.Perez | NPSH available should exceed NPSH required by at least 1.4 m (4 feet); for the