## 372-K-DAT-54002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Julio.Aguilar | Ensure the use of the project finalized cover page for the all data sheets. | Noted. It will be updated in next revision. | Y
2 | Call-out | 1 | Mahdi Ali | Material class for driver shall follow the Pump, i.e. 'G' and not 'K'. Change this across the whole document | No. K is for steam turbine driver document according to tagging procesure. | N
3 | Text Box | 1 | Jeung.Kim | Seong Jin Lee | Noted. | Y
4 | Callout | 1 | Julio.Aguilar | Steam turbine tag number to be aligned with the new numbering proposed for the new greenfield unit 370. | Noted. Item no. is changed to 370T0008A/B. | Y
5 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status. | Noted. | Y
6 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used. | Noted. Template will be updated in next revision. | Y
7 | Callout | 2 | Sankara | 115 V AC | Noted. | Y
8 | Text Box | 2 | hyunjin.paeng | Bearing & Lub.system to be confirmed by vendor | Antifriction bearing cannot be used according to BMPS-K5. 6.10.1.1- ADD Antifriction radial bearing in horizontal turbines are not acceptable. Lube oil system type will be confirmed by vendor. | N
9 | Text Box | 3 | hyunjin.paeng | Nozzle rating and face to be specified | It will be updated in next revision. | N
10 | Text Box | 3 | Jong.Ahn | Please clarify "No" means that no need the probes, no need monitors for the probes or no need the probes or monitors since it shall be supplied by others. | Noted. Probe will be supplied by vendor. Monitor will be supplied by JV. | Y
11 | Text Box | 4 | hyunjin.paeng | Over speed trip to be checked | Noted. It is mechanical type thus 2oo3 is deleted. | Y