## 372-K-DAT-54005-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Julio.Aguilar | Ensure the use of the project finalized cover page for the all data sheets. | noted. Revised template will be used in Rev_C | N
2 | Text Box | 1 | Jeung.Kim | Seong Jin Lee | -
3 | Callout | 1 | Julio.Aguilar | Turbine tag number to be revised as per the final numbering approved. | noted. | Y
4 | Cloud+ | 1 | Ebrahim.Deyab | Equipment number are different from the FEED, PID No. 2520-u372-PID-0031-055-01 Sht 44 and 2520-u372-PID-0031-065-01 Sht 54 the turbines tag number are 372T3742 A/B . Please verify | Motor / Turbine Tag no. revised by COMPANY. 372T3742 to 372T3762. Finally revised 370T0009 | Y
5 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used. | noted. Revised template will be used in Rev_C | N
6 | Call-out | 1 | Mahdi Ali | Material class shall be changed to 'G' since the Turbine shall follow the pumps. This change shall be across the whole document | SOC confirmed that G is correct for pump driver material class | N
7 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status. | noted. | Y
8 | Callout | 2 | hyunjin.paeng | Pump tag number to be revised as per the final numbering approved for the units 370/372. | noted. | Y
9 | Text Box | 2 | hyunjin.paeng | To be defined/confirmed by vendor | To be confirmed by Vendor. | Y
10 | Callout | 2 | Sankara | Confirm this as 115V AC | noted. | Y
11 | Text Box | 2 | hyunjin.paeng | To be specified | noted. | Y
12 | Cloud+ | 2 | Aamer.Hubail | oil mist not suitable for sleeve bearings | To be confirmed by Vendor. | N
13 | Text Box | 3 | hyunjin.paeng | Sentinel warning v/v to be provided | It will be updated in next revision. | N
14 | Cloud+ | 3 | Jong.Ahn | Please clarify " No" means that the probes no need to be supplied or monitoring provisions no need to be supplied by Turbine vendor. | It will be updated in next revision. | N
15 | Text Box | 3 | hyunjin.paeng | Nozzle rating & face to be specified | It will be updated in next revision. | N
16 | Text Box | 4 | hyunjin.paeng | Over speed trip to be rechecked | Mechanical Type used. Deleted 2oo3 | Y
17 | Cloud+ | 4 | Aamer.Hubail | Peak 150 has been superseded by Peak 200 | noted. | Y