## 372-K-DAT-54005-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Julio.Aguilar | Ensure the use of the project finalized cover page for the all data sheets.
2 | Text Box | 1 | Jeung.Kim | Seong Jin Lee
3 | Callout | 1 | Julio.Aguilar | Turbine tag number to be revised as per the final numbering approved.
4 | Cloud+ | 1 | Ebrahim.Deyab | Equipment number are different from the FEED, PID No. 2520-u372-PID-0031-055-01 Sht 44 and 2520-u372-PID-0031-065-01 Sht 54 the turbines tag number are 372T3742 A/B . Please verify
5 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
6 | Call-out | 1 | Mahdi Ali | Material class shall be changed to 'G' since the Turbine shall follow the pumps. This change shall be across the whole document
7 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
8 | Callout | 2 | hyunjin.paeng | Pump tag number to be revised as per the final numbering approved for the units 370/372.
9 | Text Box | 2 | hyunjin.paeng | To be defined/confirmed by vendor
10 | Callout | 2 | Sankara | Confirm this as 115V AC
11 | Text Box | 2 | hyunjin.paeng | To be specified
12 | Cloud+ | 2 | Aamer.Hubail | oil mist not suitable for sleeve bearings
13 | Text Box | 3 | hyunjin.paeng | Sentinel warning v/v to be provided
14 | Cloud+ | 3 | Jong.Ahn | Please clarify " No" means that the probes no need to be supplied or monitoring provisions no need to be supplied by Turbine vendor.
15 | Text Box | 3 | hyunjin.paeng | Nozzle rating & face to be specified
16 | Text Box | 4 | hyunjin.paeng | Over speed trip to be rechecked
17 | Cloud+ | 4 | Aamer.Hubail | Peak 150 has been superseded by Peak 200