## 373-A-PID-00026-001-R4A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Pen | 1 | Edgardo | )
2 | Pen | 1 | Edgardo | /
3 | Text Box | 1 | Mahdi Ali | Add the above note below the drawing number as was originally provided by Bapco. Do not remove this note from all the PID provided by Bapco.
4 | Text Box | 1 | Mahdi Ali | BAPCO LEGACY DRAWING NO. BRA069977 SHEET 1
5 | Call-out | 1 | MAK | Check spelling
6 | Call-out | 1 | MAK | Move this to the second line of the title.
7 | Call-out | 1 | Edgardo | Please transfer the check valves downstream of the B/L valves
8 | Call-out | 1 | Mahdi Ali | RETAIN EXISTING INFORMATION. THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS