## 374-A-PID-00001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | MODIFICATIONS TO BAPCO EXISTING DRAWINGS SHALL BE CLOUDED AS PER BMPS-A8 SECTION 5.4.1 ITEM 7
2 | Text Box | 1 | Syed Ahmed | #2HDU
3 | Call-out | 1 | Hasan Al Noaimi | 1HDU DECOMMISSIONED IN 2007. Put a note to reflect this.
4 | Cloud+ | 1 | MAK | Change to P&ID on all sheet
5 | Text Box | 1 | Syed Ahmed | Check and confirm that the new 2HDU Diesel Rundown Cooler cooling water supply from the main and secondary cooling water of BMP and update the drawing and note 2 accordingly.
6 | Call-out | 1 | Hasan Al Noaimi | CW
7 | Call-out | 1 | Hasan Al Noaimi | Delete
8 | Call-out | 1 | Hasan Al Noaimi | No3 SRU
9 | Call-out | 1 | Hasan Al Noaimi | PSIA
10 | Callout | 1 | Mahdi Ali | THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
11 | Text Box | 1 | seongjin.lee | The cooling water supply source and its tie-in points have not been finalized yet, and so the IBD drawing shall be verified and then updated & resubmitted after finalization. However, considering the urgency of IDD drawing submission, this is approved as Code 2 subject to the submission of interim revision (Rev.A1) for advance review before IDD. As agreed, the integrated comments will be delivered by joint P&ID MOM.
12 | Text Box | 1 | Mahdi Ali | THIS DRAWING WAS PROVIDED AS REV '5'; THUS THIS DRAWING SHALL BE REV '5A'