## 907-A-PID-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | Page 1 | Edgardo | Please revise stream name to read "#544 Butane"
2 | Call-out | Page 1 | Edgardo | Please revise stream name to read "#545 Propane"
3 | Call-out | Page 1 | Edgardo | These PID drawing numbers are changed; please indicate the latest assigned drawing numbers
4 | Call-out | Page 1 | Edgardo | There are no Hold items in this PID; Please consider deleting this legend from this PID
5 | Text Box | Page 1 | Edgardo | It is suggested to incorporate Notes 6, 7 & 9 in Note 8; As discussed, tie-in schedule of each line may not be the same as the process units shutdown; Owner and Contractor will discuss and define the tie-in schedule based on the availability of the lines and possible system shutdown schedule
6 | Text Box | Page 1 | Mahdi Ali | CHANGE THE OFF-PAGE CONNECTORS IN THIS DRAWING AS PER THE BELOW TABLE
7 | Typewritten Text | Page 1 | Nabeel | Should be #545
8 | Call-out | Page 1 | MAK | Correct spelling