## 907-L-INX-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
5 | Text Box | 1 | Mahdi Ali | THIS IS AN EXISTING UNIT. TTSJV SHALL QUANTIFY THE AMOUNT OF LINE NUMBERS REQUIRED FOR EACH FLUID CODE AND OFFICIALLY REQUEST THE LINE NUMBERS FROM BAPCO. BAPCO SHALL PROVIDE THE REQUIRED NUMBERS AND TTSJV SHALL ONLY UTILIZE THE NUMBERS PROVIDED. FAILING TO DO SO COULD RESULT IN DUPLICATE OF LINE NUMBERS ALLOCATED BY TTSJV FOR THE REVAMP AREA AND POSSIBLE CONFILCT WITH EXISTING LINE NUMBERS. TTSJV WILL BARE ALL RESPONSIBILITIES AND CONSEQUENCES FOR THIS.
1 | Text Box | 2 | MAK | Add page no X/Y on all pages
2 | Callout | 2 | A Albalooshi | General Comment: This document shall be updated based on final line sizing calculation. Almost all lines are on HOLD status in the P&IDs.
3 | Call-out | 2 | Edgardo | Please clarify; the test pressure type is shown as H but no test pressure was indicated
4 | Call-out | 2 | Edgardo | Please use dot "." instead of comma to represent the decimal place. Refer to Clause 4.5.1 of BMPS- A8