## 930-A-PID-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | Change in all sheet to: INTERCONNECTING SYSTEMS - BMP PLANTS
2 | Callout | 1 | Mohamed Ayyash | Space
3 | Call-out | 1 | Edgardo | This is S/U Cold VGO in 930-A-PID-00001-002; please confirm
4 | Callout | 1 | alexis.martinez | As per FEED P&ID Kero (NNF) line from 7CDU joint the line to 1RHCU of Kero Cutterstock (930-4"-P-0078-B30-N). Review and correct as required.
5 | Cloud+ | 1 | Mohamed Ayyash | Change to "Atmos"
6 | Callout | 1 | alexis.martinez | As per FEED P&ID the Diesel from 7CDU is injected in the line of Start-Up Diesel to 1RHCU. Review and correct as required.
7 | Callout | 1 | alexis.martinez | As per FEED P&ID the mixing point for Sour LPG to SGP from the other process units is upstream the split point to both SGP units which is not the case shown in the current P&ID. Same situation happens for Off Gas stream. Review and correct as required.
8 | Callout | 1 | Mohamed Ayyash | Space
9 | Callout | 1 | Mohamed Ayyash | Space
10 | Callout | 1 | alexis.martinez | As per FEED P&ID the line size of Heavy Naphtha from 7CDU is 8". Review and correct as required.
11 | Call-out | 1 | Edgardo | Please confirm this arrow head; It will not be applicable if the flow in this line is bidirectional
12 | Text Box | 1 | A Albalooshi | General comment: All applicable comments generated and agreed upon during the Joint PID Review between ROC and Owner shall be incorporated in the next update of the respective documents.
13 | Callout | 1 | alexis.martinez | As per FEED P&ID the Start-Up Diesel/Flushing Oil to 7CDU/VDU is 8". Review and correct as required.
14 | Cloud+ | 1 | Mohamed Ayyash | Change to "Atmos"
15 | Callout | 1 | Mahdi Ali | INCOMPLETE UNIT DESCRIPTION
16 | Callout | 1 | Mohamed Ayyash | Space
17 | Callout | 1 | alexis.martinez | As per FEED P&ID SR MVGO/HVGO direct to 1RHCU (NNF line) from 7CDU/VDU, joint the line to 1RHCU of S/U Cold VGO instead of S/U Naphtha as shown on current P&ID. Review and correct as required.
18 | Callout | 1 | Mohamed Ayyash | Space
19 | Callout | 1 | alexis.martinez | Move wild naphtha from !RHCU to SGP before the unstabilized naphtha to SGP is split.
20 | Callout | 1 | Mahdi Ali | OMIT THE WORD 'NEW' AS PER BMPS-A8 APPENDIX 'B' SECTION 'D'.
21 | Callout | 1 | Mohamed Ayyash | Space
22 | Callout | 1 | Mohamed Ayyash | Space
23 | Callout | 1 | Mohamed Ayyash | Space
24 | Cloud+ | 1 | MAK | On all sheets, move it from the first line
25 | Call-out | 1 | Edgardo | Please change to Resid
26 | Cloud+ | 1 | Mohamed Ayyash | Change to "Atmos"
27 | Text Box | 1 | MAK | All Unit Nos and Names stated in Unit 930 P&IDs shall be revised and corrected.