## 930-A-PID-00003-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | 356 - 6DESAL 357 - 7DESAL 358 - 8DESAL
2 | Cloud+ | 1 | MAK | INTERCONNECTING SYSTEMS FOR REVAMPING AREAS
3 | Text Box | 1 | MAK | General Comment: Use the latest drawing borders that are part of the Homogenisation Procedure.
4 | Callout | 1 | alexis.martinez | GENERAL: As per FEED P&ID the drinking water is buried line and. Review, the current P&ID shows the line in trench
5 | Callout | 1 | Mahdi Ali | REFINERY GAS SYSTEM
6 | Cloud+ | 1 | MAK | Retain the default text style
7 | Cloud+ | 1 | Khalid | More segregation stations to be considered to avoid isolation of multiple units during leaks/repairs
8 | Callout | 1 | Mahdi Ali | AIR COMPRESSORS & DRYERS
9 | Call-out | 1 | Edgardo | Instead of box, show this as standard B/L symbol
10 | Cloud+ | 1 | MAK | Make sure to use the correct Unit No. and Name. Change this everywhere to: 083 - 1N2 PLANT
11 | Call-out | 1 | Edgardo | Missing PID number
12 | Text Box | 1 | A Albalooshi | General comment: All applicable comments generated and agreed upon during the Joint PID Review between ROC and Owner shall be incorporated in the next update of the respective documents.
13 | Callout | 1 | Mahdi Ali | CWT