## 930-A-PID-00007-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Francis L | Remove the L alarms. Typical and applies to all similar tags.
2 | Callout | 1 | Francis L | Tag as A,B,C left to right.
3 | Callout | 1 | Francis L | Remove the L alarms. Typical and applies to all similar tags.
4 | Text Box | 1 | A Albalooshi | General comment: All applicable comments generated and agreed upon during the Joint PID Review between ROC and Owner shall be incorporated in the next update of the respective documents.
5 | Cloud+ | 1 | Mohamed Ayyash | CWT
6 | Callout | 1 | Mahdi Ali | 310 - 10HP BOILER 311 - 11HP BOILER
7 | Callout | 1 | Mahdi Ali | 036 - 2BAGRU 037 - 3BAGRU 041 - 5SRU 042 - 6SRU 043 - 7SRU 044 - 3TGTU 045 - 4TGTU 046 - 5SWS 047- 6SWS 048 - 2ARU 049 - 3ARU
8 | Callout | 1 | Francis L | Clarify whether this is on new DCS (FF signal)
9 | Callout | 1 | Mahdi Ali | CWT
10 | Callout | 1 | Mahdi Ali | 6DESAL 7DESAL 8DESAL
11 | Callout | 1 | Mahdi Ali | INTERCONNECTING SYSTEMS FOR REVAMPING AREAS
12 | Callout | 1 | Mahdi Ali | AIR COMPRESSORS & DRYERS