## 930-A-PID-00008-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Edgardo | Please clarify these new cooling water lines; if these are for the feed booster pump area, then these will be to Unit 934
2 | Callout | 1 | Mahdi Ali | 036 - 2BAGRU 037 - 3BAGRU 041 - 5SRU 042 - 6SRU 043 - 7SRU 044 - 3TGTU 045 - 4TGTU 046 - 5SWS 047- 6SWS 048 - 2ARU 049 - 3ARU
3 | Callout | 1 | Mahdi Ali | CWT
4 | Callout | 1 | Mahdi Ali | AIR COMPRESSORS & DRYERS
5 | Callout | 1 | alexis.martinez | GENERAL: As per FEED P&ID the cooling water (Supply and Return) lines are buried. The current P&ID shows the lines in trench. Review and do the required corrections.
6 | Callout | 1 | Mahdi Ali | INTERCONNECTING SYSTEMS FOR REVAMPING AREAS