## 930-A-PPN-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | UNIT NO. 085
2 | Cloud+ | 1 | MAK | UNIT NO. 010/011
3 | Callout | 1 | Mahdi Ali | ALL ELEVATIONS SHALL BE IN METERS AND NOT mm
4 | Cloud+ | 1 | MAK | UNIT NO. 019
5 | Cloud+ | 1 | MAK | UNIT NO. 012
6 | Cloud+ | 1 | MAK | PED
7 | Cloud+ | 1 | MAK | UNIT NO. 018
8 | Cloud+ | 1 | MAK | UNIT NO. 021/023
9 | Cloud+ | 1 | MAK | PLAN, ELEVATION & DETAILS
10 | Callout | 1 | Mahdi Ali | QUOTE THE COMPLETE DRAWING NUMBER
11 | Cloud+ | 1 | MAK | UNIT NO. 017
12 | Cloud+ | 1 | MAK | INTERCONNECTING SYSTEMS BMP PLANTS
13 | Text Box | 1 | MAK | General Comment: Use the word UNIT instead of PLANT
14 | Cloud+ | 1 | MAK | 930 - INTERCONNECTING SYSTEMS - BMP PLANTS
15 | Call-out | 1 | Mohamed Aldoseri | Sheets 2&3 formatting is corrupted. This document shall be resubmitted.
16 | Cloud+ | 1 | MAK | General Comment: The text height is small. No need to reduce the text size, otherwise the column width shall be Increased.