## 930-A-PPN-00002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | CHANGE TO MASTER PLAN
2 | Callout | 1 | Mahdi Ali | INCOMPLETE DRAWING NUMBERS. SHEET (001) IS AN INTEGRAL PART OF THE DRAWING NUMBER.
3 | Callout | 1 | Mahdi Ali | INCORRECT UNIT DESCRIPTION. DO NOT USE THE WORD 'NEW'
4 | Callout | 1 | Mahdi Ali | THERE IS NO REFERENCE TO THIS NORTHING
5 | Cloud+ | 1 | MAK | 930 - INTERCONNECTING SYSTEMS - BMP PLANTS
6 | Callout | 1 | Mahdi Ali | WHAT IS PROPERTY LINE?
7 | Cloud+ | 1 | MAK | 1.7778
8 | Callout | 1 | Mahdi Ali | CONSIDER CHANGING THE DESCRIPTION AS PER NOT FOR THIS DRAWING TITLE
9 | Cloud+ | 1 | MAK | The text height is small. No need to reduce the text otherwise the column width shall be Increased.
10 | Cloud+ | 1 | MAK | Delete
11 | Cloud+ | 1 | MAK | PIPE RACKS - UNIT 930 INTERCONNECTING SYSTEMS - BMP PLANTS
12 | Cloud+ | 1 | Sameer.Ahmed | As per latest communication with SOC for the plot plan of the basins, the roads around the basins are now included under unit 930. Hence, it need to covered under the 30% covered area