## 930-A-STS-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Bapco has not received the Unit Equipment List (Item Index) for review. How to cross check the correctness/completeness of equipment numbers within this document?? Equipment List is the master index and shall be issued before issuing this document.
2 | Cloud+ | 1 | MAK | INTERCONNECTING SYSTEMS - BMP PLANTS
3 | Callout | 1 | Mahdi Ali | THIS DOCUMENT IS A CALCULATION SHEET AND NOT A STUDY. THUS THE DOCUMENT TYPE SHALL BE 'CAL' AND NOT 'STS'. CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS DOCUMENT IS A STUDY THEN THE TITLE SHOULD BE CHANGED ACCORDINGLY.
4 | Text Box | 2 | A Albalooshi | Please define the criticality rating codes i.e. A,B,C,D as a note below. Also please define the numbers of severity etc..
5 | Cloud+ | 2 | MAK | Include pumps motors: 930M0001A 930M0001B
6 | Typewritten Text | 2 | steven.coyne | Add reference to criticality procedure - 000-A-PRO-50017-001
7 | Text Box | 2 | MAK | General Comment: Equipment List for Unit 930 was not issued for review. However, this list shall perfectly match Unit 930 - Equipment List (Item Index). All Units equipment shall be included for Criticality Rating Evaluation.
8 | Text Box | 2 | MAK | Include all the equipment and drivers in the list
9 | Text Box | 2 | A Albalooshi | Those sanitary pumps belong to unit 382. Please update the tag numbers accordingly.
10 | Cloud+ | 2 | MAK | CWT