## 930-L-INX-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | JaiMun.Oh | Please specify the following in Legend. Test Pressure : H : Hydraulic N : Not applicable P : Pneumatic Phase : L : Liquid M : Mixed V : Vapor/Gas General Notes for Line list also to be specified in Legend. General Notes 1. Piping Class Spec refer to BMPS-L2. 2. For insulation type and insulation thickness refer to BMPS-N1. 3. For paint code refer to BMPS-B5. The definition for the following to be specified in detail. - Authority Control (Phase, Group, Categ, PSxDN) - Notes for M&T - any others
2 | Callout | 1 | Berik.Nurbolatov | Legend list /sheet should be provided.
3 | Cloud+ | 1 | MAK | INTERCONNECTING SYSTEMS - BMP PLANTS
4 | Callout | 2 | Berik.Nurbolatov | PWHT
5 | Callout | 2 | Yousif Ahmadi | No C6S in BMPS-L2. Check and confirm
6 | Callout | 2 | Mahdi Ali | LINE NUMNER SHOULD NOT INCLUDE THE FLUID CODE
7 | Callout | 2 | Yousif Ahmadi | No D3S in BMPS-L2. Check and confirm
8 | Callout | 2 | Berik.Nurbolatov | Please provide process/utility line/equipment data.
9 | Callout | 2 | Berik.Nurbolatov | P&ID
10 | Callout | 2 | JaiMun.Oh | Contractor to confirm that design pressure and design temperature of the lines should not exceed the maximum pressure and temperature limit of pipe spec.
11 | Text Box | 2 | MAK | Add Bapco Doc. No. on all pages
12 | Callout | 2 | Berik.Nurbolatov | Corrosion allowance data/ header should be provided
13 | Callout | 2 | Berik.Nurbolatov | No A/U provided as a location reference. Please use AG/UG instead.
14 | Text Box | 11 | A Albalooshi | Line sizes in the P&IDs are preliminary and this shall be finalized along with Hydraulic calculations during detailed engineering stage of the EPC “The sizes are minimum in the P&IDs”. This document shall be updated after unfreezing the “HOLD” from the P&IDs.