## 930-P-CRD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Mohamed Aldoseri | INCLUDE TYPICAL INSTALLATION DRAWING
2 | Call-out | 1 | Mohamed Aldoseri | 33kV MAIN SUBSTATION
3 | Text Box | 1 | Mohamed Aldoseri | 50
4 | Call-out | 1 | Mohamed Aldoseri | EARTHING CONDUCTOR
5 | Call-out | 1 | Mohamed Aldoseri | FO CABLE
6 | Text Box | 1 | Mohamed Aldoseri | GENERAL NOTE: REFLECT THE FULL DRAWING FROM THE TYPICAL INSTALLATION STANDARD
7 | Text Box | 1 | Mohamed Aldoseri | HV CABLE LAYING IN BURIED TRENCH UNPAVED AREA
8 | Text Box | 1 | Sankara | Inncorrect description
9 | Callout | 1 | Berik.Nurbolatov | Please show electrical duct bank location on the map. Only Electrical legend is shown here.
10 | Call-out | 1 | Mohamed Aldoseri | PROVIDE SECTIONAL REFERENCE ON THE CABLE ROUTE PLOT (A-A)
11 | Text Box | 1 | Jongman.Kim | Warning Tape
12 | Call-out | 1 | Mohamed Aldoseri | WRONG LOCATION