## 930-S-CAL-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | INCOMPLETE UNIT DESCRIPTION
2 | Callout | 1 | Mahdi Ali | REPLACE WITH '-'. FOR THE APPROVED UNIT DESCRIPTION, REFER TO THE HOMOGENIZATION PROCEDURE.
3 | Cloud+ | 3 | Mohamed Ayyash | Avoid spaces between letters.This paragraph needs to be rewritten.
4 | Callout | 3 | Mohamed Ayyash | effluent
5 | Callout | 3 | Mohamed Ayyash | flows
6 | Callout | 3 | Mohamed Ayyash | flows
7 | Text Box | 4 | Antony.Bentley | ADD REFERENCE TO TTSJV JDS DOCUMENT : 000-S-TSP-50001-001 - DRAINAGE SEWER SYSTEMS & EFFLUENT TREATMENT
8 | Cloud+ | 4 | Mohamed Ayyash | Align
9 | Callout | 4 | Mohamed Ayyash | Correct
10 | Text Box | 5 | Bader Abdulrahman | SI Units?
11 | Callout | 6 | Mohamed Ayyash | Delete space
12 | Callout | 6 | Mohamed Ayyash | Delete space
13 | Callout | 6 | Mohamed Ayyash | Delete space
14 | Cloud+ | 6 | Mohamed Ayyash | Delete spaces
15 | Callout | 6 | Chandrahasan D | m3/hr
16 | Callout | 6 | Mohamed Ayyash | process
17 | Callout | 6 | Mohamed Ayyash | Space
18 | Callout | 6 | Mohamed Ayyash | Space
19 | Callout | 6 | Mohamed Ayyash | Space
20 | Text Box | 7 | Antony.Bentley | Add reference to software used to calculate design flows/pipe sizes etc.
21 | Cloud+ | 7 | Mohamed Ayyash | Correct
22 | Callout | 7 | Mohamed Ayyash | Correct
23 | Cloud+ | 7 | Mohamed Ayyash | Overlap, Correct and align text
24 | Text Box | 9 | Antony.Bentley | THE OUTPUT ON PAGES 14-17 IS DERIVED FROM WHAT SOFTWARE ? IF IT IS DERIVED FROM AN INTERNALLY (TTSJV PARTNER) PREPARED SPREADSHEET & NOT RECOGNISED PROPRIETORY SOFTWARE THEN A VALIDATION/VERIFICATION EXERCISE SHALL BE UNDERTAKEN BEFORE THE RESULTS CAN BE ACCEPTED AS CORRECT.
25 | Cloud+ | 10 | Mohamed Ayyash | Overlap
26 | Cloud+ | 10 | MAK | Use Bapco doc no. for references.
27 | Callout | 10 | mohamed.alaradi | Where is the tanks area drainage branch??
28 | Cloud+ | 11 | MAK | Delete
29 | Callout | 11 | mohamed.alaradi | what about new crude tanks??
30 | Cloud+ | 12 | MAK | Delete
31 | Callout | 14 | Mohamed Ayyash | Use decimal points on all figures in the table