## 932-A-PID-00010-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | 2
2 |  | 1 | User | 932 - SULPHUR BLOCK UNIT
3 | Cloud+ | 1 | MAK | Change to P&ID on all sheet
4 | Cloud+ | 1 | MAK | COMMON AREAS FOR 3 SULPHUR PLANT
5 | Text Box | 1 | Mahdi Ali | FOR FIRE HYDRANTS 'FH' THE SEQUENCE NUMBERS ARE ALREADY ALLOCATED BY BAPCO. THE SEQUECE NUMBERS ALLOCATED FOR THE BMP PROJECT IS FROM 2,000 TO 5,000 AND THEY SHALL BE UTILIZED BY TTSJV. THOSE NUMBERS SHALL BE USED REGARDLESS THE UNIT NUMBERS AND THEY SHALL NOT RESET TO 0001. TTSJV SHALL COORDINATE THE MANAGEMENT OF THE SEQUENCE NUMBERS.
6 | Callout | 1 | Syed Ahmed | No.3 Sulphur Unit.
7 | Text Box | 1 | Syed Ahmed | please update the fire fighting system as per new plot plant
8 | Cloud+ | 1 | MAK | Use the correct no.