## 000-A-PRO-50079-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 5 | Nalini Mohan | Disposition plan shall be approved by OWNER.
2 | Callout | 5 | Jeung.Kim | please provide detail procedure for the reporting of NCR to Owner and Owner involvement in the disposition and verification of closing out.
3 | Callout | 5 | Jeung.Kim | Provide these for each OC. Please detail how to apply each OC procedure for the common JV activity of procurement and construction
4 | Text Box | 5 | Ahmed Bucheeri | Shall