## 000-C-GRD-70003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | Typo, Should read No. (apply to all sheets. | Noted. It will be updated in revision A | Y
2 | Text Box | 1 | MAK | Use the latest cover page template that is part of the Homogenization Procedure. MOC shall coordinate with JV Directorate. | TTSJV is checking Owner comments to all Material Requisitions and the templates will be revised accordingly to be implemented in the OC deliverables. | N
3 | Cloud+ | 1 | Adnan Alothman | All vessels listed in this MR are CS vessels. TR to check and modify the title | This title is preffered in case a SS vessels need to be quoted in a future | N
4 | Text Box | 1 | Raj | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3. | Noted.
5 | Callout | 3 | Adnan Alothman | General: As per the Contract, Annex1-Technical documents do not have any order of precedence. Please correct this to align with EPC Contract. | Noted. It will be updated in revision A | Y
6 | Call-out | 7 | Ahmed Marhoon | What about bridles for level instruments? | No instrument part is included in this requisition | N
7 | Callout | 14 | Mohamed Ayyash | Should read "Commissioning and Start-up" not vise versa. | Noted. It will be updated in revision A | Y
8 | Callout | 14 | Mohamed Ayyash | Add "Commissioning" to the sentence (missing) | Noted. It will be updated in revision A | Y
9 | Callout | 15 | Mohamed Ayyash | Add space between paragraphs | Noted. It will be updated in revision A | Y
10 | Callout | 15 | Mohamed Ayyash | Add space between subheading and paragraph in line with others. | Noted. It will be updated in revision A | Y
11 | Callout | 15 | Mohamed Ayyash | Is commissioning phase included ? | TTSJV is checking Owner comments to all Material Requisitions and the templates will be revised accordingly to be implemented in the OC deliverables. | N
12 | Callout | 16 | Mohamed Ayyash | Add space between heading and paragraph in line with others. | Noted. It will be updated in revision A | Y