## 000-E-SOW-70001-001
ID Nº | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Stamp |  | Raj |  |  | -
2 | Cloud+ |  | Yousif | Correct the description of 019E0005A/B to be 1st Stage…… | Updated | Y
3 | Call-out |  | Yousif | 019E0006A/B are missing from the list | Updated | Y
4 | Cloud |  | Sameer Foujdar |  |  | -
5 | Callout |  | Sameer Foujdar | Correct the description of 019E0004A/B to be 1st Stage Reactor Feed Effluent Exchanger. | Updated | Y
6 | Cloud |  | Sameer Foujdar |  |  | -
7 | Callout |  | Sameer Foujdar | This exchanger are 019E0011A & 019E0011B. Presently using the FEED documents. |  | Y
8 | Callout |  | Sameer Foujdar | Gas | Updated | Y
9 | Callout |  | Sameer Foujdar | Effluent/Recycle | Updated | Y
10 | Callout |  | Sameer Foujdar | delete no 7 | Updated | Y
11 | Arrow |  | Sameer Foujdar |  |  | -
12 | Text Box |  | Hasan Asad | Add: Spares for T&I inspection and overhaul. | N/A | N
13 | Text Box |  | Hasan Asad | Basis exchanger type; DEU or modified DEU. | TEMA Type considered as follows: • Modified DEU ("A" Style) à 019E0003/04/06/11/12 ¦ 019E0006/04/07/09/10 • DEU ("B" Style or TR Proposal if approved) à 019E0005 • DFU ("B" Style or TR Proposal if approved) à019E0008 ¦ 019E0011 | Y