## 000-G-GRD-60002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | Change to TSP for Technical Specifications
2 | Text Box | 1 | Mahdi Ali | Add title of the document in the header
3 | Callout | 1 | Fatema Hashem | DOC NUMBER IS UNCLEAR. CORRECT
4 | Call-out | 3 | Ali Abbas | In some documents capital letters are used in in others small letter. Need to standardize.
5 | Callout | 3 | rob.urban | Including Seal Oil Dryer/Coalescer and Seal Oil Injection Pumps if they are part of the MR
6 | Callout | 3 | Fatema Hashem | TTSJV
7 | Call-out | 4 | MAK | General Comment: Owners document/drawing numbers along with the title shall be used for any references in any document and drawing.
8 | Callout | 4 | rob.urban | The supplier of the Ebullating Pumps will be Flowserve. So this Requisition will only be sent to Flowserve. They will need to subcontract out the other items.
9 | Text Box | 4 | rob.urban | In previous LC Finers the Seal Oil Dryer/ Coalescer Skid and Seal Oil Injection Packages were not included in the scope of Flowserve but were requisitioned separately. This means that Flowserve needs to coordinate all interface points which might be a risk.
10 | Text Box | 5 | Mahdi Ali | In addition to 2D GA drawings and sections and all other related docs/dwgs as per CDRL.
11 | Call-out | 5 | Ali Abbas | Please ensure data sheet reflect all instrumentation and MCM requirements as per applicable BMPS A3 and other J spec.
12 | Call-out | 5 | Ali Abbas | Training requirements to be added.
13 | Text Box | 6 | Hasan Asad | This shall be under OEM/Vendor supervision.
14 | Text Box | 6 | Hasan Asad | These activities shall be supervised by OEM/Vendor.
15 | Call-out | 6 | Ali Abbas | Owner Representative to be added part of attendees for all activities below. General comment.
16 | Call-out | 6 | Ali Abbas | CHAZOP study to be added and to be attended by EPC/Vendor/Owner
17 | Call-out | 6 | Ali Abbas | and IFAT
18 | Call-out | 6 | Ali Abbas | Control Narratives
19 | Text Box | 6 | Hasan Al Noaimi | owner's operations and maintenance to attend from 1 to 7
20 | Call-out | 7 | Ravi Kumar | Ebullating Pumps are on sole vendor basis CLG/BMP vendor list
21 | Text Box | 7 | Mahdi Ali | and auxiliaries
22 | Text Box | 7 | rob.urban | Seal Oil Dryer/Coalescer and injection pumps will most likely be different suppliers/vendors but under the responsibility of Flowserve according to this requisition
23 | Call-out | 7 | Ali Abbas | Applicable BMPSs, CDRL and Typical and Standard drawings for instrumentation to be provided for all package vendor to follow. This is general for all requisitions.
24 | Text Box | 8 | Ravi Kumar | Please add the following under specific requirements: Vendor to refer to Section 5.11 of BMPS-G1 and comply with requirements relating to Ebullating Pumps Thermal analysis requirements
25 | Call-out | 9 | Ravi Kumar | Add ASME Sec VIII Div. 2 also. CLG specification states fabrication reqmts to meet Div2 reqmts
26 | Text Box | 10 | Mahdi Ali | (s)
27 | Text Box | 11 | Mahdi Ali | All drawings and documents shall quote Bapco numbering system
28 | Text Box | 12 | Hasan Asad | OEM/Supplier shall provide LCCA for 20 years as to understand the reliability expectation for components level.
29 | Text Box | 12 | Hasan Asad | Pump & Motor for direct replacement.
30 | Text Box | 13 | Hasan Asad | Due to speciality of this pump application, the Supplier/OEM shall provide scope of work with rates for the long term service agreement with the Owner.