## 000-G-ITP-60001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Rashed Almudahka | General note a lot of deviations were found in the submitted ITP from BMPS-G-50309. Contractor shall provide a list with all deviations with proper clarification/ explanation.
2 | Call-out | 2 | Rashed Almudahka | shall be review (R) as per BMPS-G-50309
3 | Call-out | 2 | Rashed Almudahka | shall be hold (H) as per BMPS-G-50309
4 | Callout | 3 | Isamu | including NPSHR test
5 | Call-out | 7 | Rashed Almudahka | shall be review (R) as per BMPS-G-50309
6 | Call-out | 7 | Rashed Almudahka | shall be witness (W) as per BMPS-G-50309
7 | Call-out | 8 | Rashed Almudahka | shall be witness (W) as per BMPS-G-50309
8 | Text Box | 15 | Hasan Asad | Mechanical over speed trip test & functionality.
9 | Text Box | 15 | Hasan Asad | W