## 000-K-GRD-70001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Raj | Owner has reviewed and commented on the MR package submitted on Contractor’s request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3. | Noted
2 | Text Box | 1 | Mahdi Ali | Add document title in the header | It will be standardized by Directorate | N
3 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all sheets | Not aplicable. This is not a typo mistake | N
4 | Callout | 1 | Mohamed Ayyash | What is 000M? should be 7CDU/2HCU | Not applicable. This is a generic designation of the document assigned by TTSJV DCC and cannot be modified. | N
5 | Text Box | 1 | Mahdi Ali | Add equipment numbers | Tag numbers are include in the SOW that is part of this document, please note that is some requisitions are too many items to be included in a cover sheet. | N
6 | Call-out | 3 | Ahmed Marhoon | Ensure Licensor's mandatory technical requirements are also addressed/met. | Applicable BMPS J specifications are already included in the MR. Nevertheless, please note that it is a SUPPLIER responsibility to ask for any documents called for in the attached documents, which PURCHASER may unintentionally have omitted to mention in the Material Requisition | N
7 | Callout | 3 | Adnan Alothman | As per the Contract, Annex1-Technical documents do not have any order of precedence. Please correct this to align with EPC Contract. | It will be checked and modified by JV in order to be implemented in the template. Vendor will be advise during TBE stage | N
8 | Call-out | 4 | Sameer Foujdar | Supplier shall provide startup procedure along with logic sequence and pre startup requisites. | Noted. This information is already requested as part of Vendor and drawings and data requirements. | N
9 | Text Box | 4 | Hasan Asad | 1. The vendor shall provide LCCA report considering Complete Compressor unit and major equipment. 2. The vendor shall provide maintenance manual with troubleshooting guideline for complete Compressor unit and sub-system such as lube oil, etc. | It´s in CONTRACTOR deliverable. Vendor only supply the information to preapre the LCCA | N
10 | Callout | 4 | Yousif Ahmadi | Remove M so it should read 000-K-ITP-70001-001 | Noted. Modification will be included document revision | Y
11 | Callout | 4 | alexis.martinez | Add "Scope of Supply document" | Noted. Modification will be included document revision | Y
12 | Call-out | 4 | Ahmed Marhoon | What about ESD? | Not applicable. Note that there is not interaction between package scope and ESD. Interaction between ESD and DCS is on Contractor scope. | N
13 | Callout | 4 | Adnan Alothman | For all critical equipment, company representative attendance is required as per BMPS-B11. | It will be checked and modified by JV in order to be implemented in the template. Vendor will be advise during TBE stage. | N
14 | Call-out | 5 | A.Jabbar Mahmood | What about owner representatives? | It will be checked and modified by JV in order to be implemented in the template. Vendor will be advise during TBE stage | N
15 | Call-out | 5 | Ahmed Marhoon | Change FAT to IFAT. Also, what about ESD? | I-FAT is not applicable to this RFI. ( there are no control systems in VENDOR scope) | N
16 | Call-out | 5 | Ahmed Marhoon | Add CHAZOP | CHAZOP is not applicable to this RFI. ( PLC or MMS is not VENDOR scope). VENDOR scope is limited to sensors probes. | N
17 | Cloud+ | 5 | Ahmed Marhoon | These are major milestones and shall be attended by owners' representatives. List to be updated according to the project's agreed responsibility matrix. | Note that this table is only to inform VENDOR to the meetings that they need to attend. OWNER will be invited to all meetings as per CONTRACT requirements. | N
18 | Text Box | 6 | Sankara | HV Motors for Zone 2 shall be Ex-d or Ex-e only. | Noted. Modification will be included document revision. Nevertheless based on BMPS-P1 Ex-p will be offered as and option. | Y
19 | Callout | 6 | Yousif Ahmadi | Add BMPS to so it should read BMSP-K1 | Noted. Modification will be included document revision. | Y
20 | Text Box | 6 | Hasan Asad | The pulsation dampeners shall be equipped with drain facility connected to flare - Vendor experience and proposal to be requested. | Noted. Pulsation dampeners drains facility will be in accordance to applicable project specification BMPS-K1 as indicated on this RFI and applicable project specification. | N
21 | Callout | 7 | Mohamed Ayyash | General comment: Replace with tabs in all sheets | Noted . " - " will used instead. | Y
22 | Text Box | 8 | Hasan Asad | Required | As required on API 618 and applicable project specification BMPS-K1, final requirement shall be based on VENDOR selection. Therefore if finally required. RPCW system shall be as describe on RFI. | N
23 | Call-out | 10 | Ahmed Marhoon | Scope of spill back system to be clarified. Will it be designed by others or the supplier? | Clarification. Spillback is out on VENDOR scope. Nevertheless, it will be designed in accordance to performance requirement confirmed by VENDOR. | N
24 | Call-out | 10 | Ahmed Marhoon | Refer to comment on the manual vs automatic Un-loaders given on the respective DS. | Clarification. Reference to Mechanical data sheet is already made as general consideration. | N
25 | Call-out | 10 | 986131 | Reword DCS/ESD. | Not applicable to this RFI. ( there are no control systems in VENDOR scope)
26 | Text Box | 11 | Hasan Asad | Rod Drop | Not applicable. As per BMP-K1 CMS is optional and it is not applicable to compressor package included on this material requisition. Note that Rod drop probes to be connected to MCM are already required on this document. | N
27 | Text Box | 11 | Hasan Asad | Is this Machine Condition Monitoring System - MCM System? | CMS and MCM are separated systems. | N
28 | Text Box | 11 | Hasan Asad | The Vendor/Supplier to clarify the difference between MCM and CMS and which signals will be send to each system for Owner understanding, review and approval. | Not applicable . CMS is not longer required. | N
29 | Text Box | 12 | Hasan Asad | Equipment installation shall be under Vendor supervision. | Noted. Vendor supervision is already included and considered. | N
30 | Text Box | 12 | Hasan Asad | Probes to be installed by the package vendor at the their shops meeting project specification requirement for interfacing with MCM BN. | Clarification. When possible these probes/sensor will be supplied full installed. Nevertheless note that in mos of the case Reciprocating compressor are supplied partially assembly. Therefore some probes and sensors will be supplied loose for field installation under VENDOR supervision. | N
31 | Callout | 14 | Mohamed Ayyash | Enlarge font inline with others | Noted. Modification will be included document revision. Note that reffered specification will be changed by : ASME B73.1 for Centrifugal Pumps. | Y
32 | Text Box | 15 | Hasan Asad | Such requirement shall be installed in Vendor/Supplier shop. | Clarification. When possible these probes/sensor will be supplied full installed. Nevertheless note that in mos of the case Reciprocating compressor are supplied partially assembly. Therefore some probes and sensors will be supplied loose for field installation under VENDOR supervision. | N
33 | Call-out | 15 | Sameer Foujdar | Electronics for start-up sequence logics should also be included. | Noted. This information is already requested as part of Vendor and drawings and data requirements. Additional information on this point is not applicable. | N
34 | Text Box | 15 | Hasan Asad | The Supplier shall ensure that the lube/control oil system are flushed properly to Supplier/Vendor quality control and satisfaction. | Noted. Requirement already required and considered by project specification. Additional information on this point is not applicable. | N
35 | Call-out | 15 | Ali Abbas | Including flow charts, refer to typical documentation in the ITB. | Noted. This information is already requested as part of Vendor and drawings and data requirements.Additional information on this point is not applicable. | N
36 | Callout | 18 | Mohamed Ayyash | Add space | Noted. Modification will be included document revision. | Y
37 | Callout | 19 | Mohamed Ayyash | Should read Commissioning and Start-up (not vise versa) | Noted. Modification will be included document revision. | Y
38 | Text Box | 19 | Hasan Asad | Basis Vendor PM schedule, the suction and discharge valves shall be inspected after certain hours. Hence, the Owner shall consider one complete set of suction and discharge valves as Capital Spare. | Not applicable . As per contract Attachment 1, there are not any Capital Spare required for Reciprocating Compressors. | N
39 | Callout | 19 | Mohamed Ayyash | Add "Commissioning" | Noted. Modification will be included document revision. | Y
40 | Text Box | 20 | Ahmed Marhoon | The following are comments related to instrumentation and control. Contractor is requested to update the other documents issued as part of this transmittal, in addition to the data sheet, based on the comments stated herein and ensure consistency prior to release of MR to suppliers. 1. Add a clear note on Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. Requirement of MCM to be verified with the supplier. Reference to BMPS-J15 MCM to be added. Also, all applicable BMPS-J series to be referenced (such as J2, J3, J6, J31 …etc) for the supplier to comply with. 2. Instruct the supplier to source instrumentations from project AVL only. 3. Add a note to the supplier with reference to the applicable BMPS to design and supply the system according to the final PID. Functional design specifications covered in this MR shall be firmed based on the approved PID. Vendors to be clearly notified on the necessity to include all the Hazop3/SIL recommendations and changes made Post-EPC-Development. 4. Spill-back design shall be reviewed and confirmed with the supplier. Contractor to consider the compressors protection and process requirements according to manufacturer and licensor recommendations. 5. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 6. All the machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. | 1. All requirements mentioned in BMPS A-3 reference section 8.5MCM will be included in MR and Mechanical Data Sheet. It will be checked during Technical Bid Evaluation stage 2. Noted. See attachment 1 3. Final P&ID will be submitted by Pump Vendor, including all its scope and approved by CONTRACTOR. CONTRACTOR will check that HAZOP actions shall be correctly implemented. All BMPS applicable are part of the Material Requisition and included in section named MRQ. 4. Clarification. Spillback will be designed and sized by CONTRACTOR based on process and compressor requirements.. 5. It is under discussion with JV Directorate (instrumentation) Vendor will be informed with final decision to standardize which instruments are required wireless. 6. When possible these probes/sensor will be supplied full intalled.Refers to item 32 above | N
|  |  |  | 7. Narrative/flow charts/cause and effect shall be provided for any control or sequence logic. 8. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting …etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31. 9. Supplier to be instructed to generate all instrument data sheets, hook ups ...etc. in project specs (according to Bapco standard formats) and to be developed in SPI format. Typical formats can be provided to the supplier at a later stage for compliance. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 10. Compliance to licensor's mandatory and recommended requirements to be included. 11. Supplier to comply with all the applicable BMPSs and provide, as a minimum, all the documents, hardware, software and services according to the relevant sections of the BMPSs in the agreed standard formats of the project. List to reflect all the required deliverables in accordance to BMPS. 12. Vendor/TTSJV shall provide a list of deviation from BMPS specifications, in addition to the requisition specifications, for owner's review and approval. | 7. Noted. Already included in VDDR. 8. All applicable specifications are already included in MRQ. 9. All instrument Data Sheet and any other information required for instruments is already included as required in the VDDR (MRQ). 10. All licensor and mandatory requirement are already included in each Mechanical data sheet for each item. 11. Noted. Requirement already considered and included in this requisition. If any deviations shall be clearly indicated on the applicable template fro Owner approval. 12. Refers to replied above on item 11.
41 | Callout | 20 | Mohamed Ayyash | Shouldn't this include commissioning phase as well ? | Confirmed Special tools referred on this section, includes all the special tools requires for the proper Compressor package installation and/or maintenance in all phases. | N